## Sheet1
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | Data Preprocessing | Data Preparation | I need to preprocess the CIC-DDoS2019 dataset to remove noise and scale features for model accuracy. | Must | Completed | Dataset is cleaned and scaled. Missing data is handled. Feature selection reduces dimensionality effectively. | Apply PCA, correlation analysis, and mutual information for feature selection. Perform data scaling and normalization. | Preprocessing should not distort the dataset distribution. Execution time for preprocessing should not exceed 2 minutes on the full dataset. | 15 days | 10 days
2 | KNN Model Implementation | Model Development | I need to implement the KNN algorithm for DDoS detection to establish a baseline for comparison. | Must | Completed | KNN model is trained on the preprocessed dataset. KNN accurately classifies benign and DDoS traffic with acceptable accuracy. | Implement language selection in user settings. Use localization for all UI text and content. | KNN model should classify data in under 5 seconds. Accuracy should be above 85% with the preprocessed data. | 15 days | 14 days
3 | CNN Model Development | Model Development | I need to develop a CNN model to improve detection accuracy for DDoS attacks compared to the KNN model. | Must | Completed | CNN model is trained on the same dataset. The model achieves higher accuracy and recall than KNN for complex traffic patterns. | Use TensorFlow/Keras for CNN implementation. Train CNN on GPU with multiple convolutional layers. Apply dropout to prevent overfitting. | CNN training should complete in under 10 minutes on a GPU. Accuracy should be higher than 90%, with a false positive rate below 5%. | 15 days | 12 days
4 | Hybrid Quantum Neural Network (H-QNN) | Quantum Model Integration | I want to integrate quantum computing layers with a neural network to improve efficiency in DDoS detection. | Must | Completed | H-QNN model integrates classical and quantum layers. The model demonstrates higher speed and accuracy compared to CNN and KNN. | Use PennyLane for quantum layers. Ensure seamless integration with classical CNN architecture. Test model using quantum backends like Qiskit. | Quantum operations should run without significant latency. Model must achieve accuracy above 92% and reduce computational time for feature extraction. | 15 days | 15 days
5 | Model Comparison and Evaluation | Results and Evaluation | I want to compare the performance of KNN, CNN, and H-QNN models using accuracy, precision, recall, and F1-score. | Must | In Progress | Detailed comparison of all models. KNN, CNN, and H-QNN models are evaluated using test data. Performance metrics are documented and analyzed. | Generate evaluation metrics (accuracy, precision, recall, F1-score, ROC-AUC) for each model. Create performance comparison graphs and tables. | Evaluation must be completed within 2 days. Results should be reproducible and explainable for publication purposes. | 15 days | 10 days